## Progress Tracker
Agri-Tech-Farm Water Management
| GL Action Plan | Our Action Plan
2021-10-18 | Project Start
2021-10-19 |  | 1. Architecture Diagram 2. Internally tryout the architecture implementation and see if this is feasible to complete the Basic Requirement for the project 3. Have a call with the team to discuss and finalize atchitecture to present it in mentor session
2021-10-20
2021-10-21
2021-10-22
2021-10-23 |  | 1. Start working to finalize the Basic Requirements based on the final atchitecture
2021-10-24 | Mentor Session 1 |  | DONE
2021-10-25
2021-10-26
2021-10-27
2021-10-28
2021-10-29 |  | 1. We can connect if all are available for discussion
2021-10-30 | Mentor session 2 | 1. Finish the all required coding for the Basic Requirement on or before this date 2. We can have a internal demo for the Basic requirement and may be take few screerecord of working demo etc.
2021-10-31 |  | 1. Finalized Advance features implementation process
2021-11-01
2021-11-02
2021-11-03
2021-11-04
2021-11-05
2021-11-06 |  | 1. Review the Advance Feature implementation progress 2. Finish the Advance Feature implementation
2021-11-07
2021-11-08 | Intermediate Milestone
2021-11-09
2021-11-10
2021-11-11
2021-11-12 |  | 1.Internal Demo for the final version 2. Documentation & Ready for submission
2021-11-13
2021-11-14
2021-11-15
2021-11-16
2021-11-17
2021-11-18
2021-11-19 | Last Submission Date
2021-11-20 | Demo Day
2021-11-21 | Demo Day

## Considerations & Questions
Consideration & questions :
-- Based on the crop determine how much the soil moister should be |  | https://soilsensor.com/soil/soil-moisture-and-irrigation/
-- Check how much we getting from sensor |  |  | Work
-- How to use weather data in decission making ? -- need clarification |  |  | Backend Coding |  | Vijayalakshmi | Karthik | Chinmoy | Joel
-- Calculate how much water required for the difference in moister |  |  | AWS Configuration + NodeRED |  | Vijayalakshmi | Karthik | Chinmoy
-- How the moister will change based on the water ? -- need clarification |  |  | User Portal UI |  |  |  | Chimoy
-- How temperature being used ? |  |  | Documentation
Tech Implementation steps :
We can use EC2 only as we are making decission on historical data. Also this is cost effective compare to Lamda
All sensor will send data to MQTT and we store those though Stream into Dynamo DB
In EC2 have cron job that will run each 5 min and create 5 jobs in SQS (as we have 5 sprinklers )
Each job, corrospond to each sprinklers, will pull the data for its 4 sensors for last 5 min and then may be if 3 among 4 sensors data cross the thresold to activate the water then only we can send ON signal to the sprinkler
Once the job made the decision , the payload pushed to MQTT and then from stream data update device status in DynamoDB
Table Schema
| devices |  |  | Assumptions
| device_id |  |  | Example :
| device_type | soil sensor (ss) or sprinkler (sp) |  | The soil is a silt, crop is Cucumber, the MAD is 50%, and the soil moisture is 20% throughout the root zone which is down to 24 cm. The sprinkler is 75% efficient. How much water should be applied?
| ss_device_ids | this will have all SS device ids with comma in case its a sprinkler deivice
| device_status |  |  | Answer:
| timestamp |  |  | From the table above, the MAD = 0.5. From the graph (or a soil survey) the permanent wilting point (θPWP) = 16% and the field capacity (θFC) is 32%. Using the three equations above, the optimal soil moisture is 24% to 32%. θFC – θ = 32% – 16% = 16%. Therefore, the soil needs to be irrigated to increase the soil moisture by 16% down to 24 cm, 16% X 24 cm = 3.8 cm of water applied.
| [ We can store the cerificate details for the things with this table if required ] |  |  | If the sprinkler is 75% efficient then 3.8 cm/0.75 = 5.12 cm of water should be applied. Note the rate of water coming out of the sprinkler should not exceed the infiltration rate of the soil and the run time of the sprinklers would depend on the specification of the sprinkler.
| soildata |  |  |  |  | Crop | Maximum Allowable Depletion (MAD) | Effective Root Depth (Inches)
| device_id |  |  |  |  | Apples | 75% | 36
| timestamp |  |  |  |  | Blueberries | 50% | 18
| value_moister |  |  |  |  | Carrot | 50% | 18
[6 empty] | Cauliflower | 40% | 18
| sprinkler_actions |  |  |  |  | Cucumber | 50% | 24
| device_id |  |  |  |  | Grass | 50% | 7
| timestamp |  |  |  |  | Green beans | 50% | 18
| status |  |  |  |  | Leafy greens | 40% | 18
| value_moister_on_action |  |  |  |  | Peppermint | 35% | 24
| value_weather_data_on_action |  |  |  |  | Potato | 35% | 35
| (just for log in case anythong goes wrong , this will help to track back the decision ) |  |  |  |  | Strawberry | 50% | 12
[6 empty] | Sweet corn | 50% | 24
Sensor | https://www.amazon.in/DIGITAL-TEMPERATURE-HUMIDITY-COMPATIBLE-ARDUINO/dp/B07FSPW4VK/ref=sr_1_8?dchild=1&keywords=Humidity+Sensor&qid=1634983946&qsid=260-8589557-6691156&sr=8-8&sres=B07V1GJFK5%2CB01LTHYX0U%2CB01MXRT9DZ%2CB07FSPW4VK%2CB0972Y182F%2CB072FJBF9T%2CB08BRYXCYZ%2CB07VVHGDQ4%2CB07W1WNDQC%2CB07HN7V2PT%2CB01AV14S00%2CB00O8RIYYU%2CB084DWRKWR%2CB07W1X5L6M%2CB07PBHBLJL%2CB083ZX655K%2CB01DM8Y8MC%2CB01HI9G9ZU%2CB07GTMRBZ8%2CB072TD6NHB |  |  |  |  | Table beet | 50% | 18
| https://robu.in/product/soil-moisture-meter-soil-humidity-sensor-water-sensor-soil-hygrometer-ardunio/ |  |  |  |  | Winter squash | 60% | 36

## Architecture Diagram
Agri-Tech-Farm Water Management
FInal Diagram - V2
Initial Diagram - V1

## Basic Requirements
Agri-Tech-Farm Water Management
The features and systems essential for the system to function are:
1 | Soil sensor and sprinkler simulators
There should be at least 20 soil sensors and 5 sprinklers, with each sensor mapped to a particular sprinkler
These should be IoT Core Things publishing and receiving information
You can run all of them under one process (if you prefer) on a local machine or an EC2 instance
(OPTIONAL) You are free to add 1, or more, real devices with temperature and moisture sensors if you have them available
2 | Air temperature and humidity information of a representative lat/long based location of the farm
You can use https://openweathermap.org/api or any equivalent API
This can be directly sent to your computing solution, via an EC2 instance, local machine, or a Lambda function
3 | AWS IoT Core to receive all the data, messaging back to the sprinklers, and passing the data further down to streaming and database entities
4 | Database in the cloud to store raw information and decisions
You can use DynamoDB (preferably) or managed MongoDB/DocumentDB/MySQL/PostgreSQL (in the cloud)
5 | Quick turnaround decision making (within 5 minutes)
You can look at a streaming and analytics solution like Kinesis along with Lambda
Another option can be code in Lambda or EC2 instance, periodically checking the latest readings in the database and acting accordingly
6 | Ability to display (text or visual) the state of various sensor and sprinkler systems

## Advance Feature
Agri-Tech-Farm Water Management
1 | The sensors and actuators could be auto-provisioned using a program that can use AWS IoT Core APIs. You should be able to set up a soil sensor or sprinkler through the command line (or through a UI) to register a thing with a unique name, with appropriate mapping. It should deliver the necessary keys and certificates for the device to connect and transfer data.
2 | Real-time visual dashboard of the activity. This can show an entity-based or a map-based view of the current sensor states and sprinkler activity
You can use an IoT dashboard like Node-red for a simple view.
You can also go for a simple but custom frontend app using Python Flask or AWS API Gateway/Lambda to serve the relevant information, in more appealing formats.
3 | Long-term processing to highlight data-based insights of the farm. This can include some of the following, and any other relevant analytics:
Areas of low and high water consumption
Water consumption trends based on air temperature and humidity
Visual representations of farm water usage patterns, with location information (pie-charts, bar-charts, bee-hives)

## Evaluation Criteria
Evaluation Criteria
The project evaluation will be based on the following criteria:
Feature completion of the basic requirements
Code and infrastructure architecture
Any advanced feature development

## Faculty Opinion
device simulator (temp/humidity/soil moisture)
MQTT broker (AWS IoT Core)
data collector (Rule)
Database (Dynamo DB)
define anomaly and exclude such anomaly data
Collect the data in a fixed interval (5 mins)
Find average, based on a threshold send an event to switch on sprinkler
log the sprinkler events and store in s3 bucket
data analysis
x -> ideal temp
y -> ideal hum
x’ -> curr temp
y’ -> curr hum
1 -> 30
2 -> 60
3 -> 45
evapotranspiration
Farmer
-> Plots
-> plot001
-> sprinkler : 2 sp001, sp002
-> sensors : 5 sen001… sen005
farmer_id, plot_id, address, location
user001, plot001, mumbai, <lat,long>
farmer_id, plot_id, device_id, device_type
user001, plot001, sp001, sprinkler ABC/iot/agri/irrigation/user001/plot001/sprinkler/event
user001, plot001, sp002, sprinkler ABC/iot/agri/irrigation/user001/plot001/sprinkler/event
user001, plot001, sen001, soil_sensors
user001, plot001, sen002, soil_sensors
user001, plot002, sen001, soil_sensors
user001, plot002, sp001, sprinkler
sensor_id, plot_id, value, timestamp
sen001, plot001, 25.8, 23/10/2021, 12:22 pm
Collect sensor data based on each plot, compare with the threshold,
and send event to the respective plot sprinklers if needed